## Sheet1
HOLY SPIRIT PUBLIC SCHOOL
Identified By: Reported By: Date: Environment Details:
Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Screenshot | Status
DEF_HSPS_01 | Should work the Login tab | login tab on the headder part is not working | 1.open the webpage 2.click on the Login tab | Critical |  |  | New
DEF_HSPS_02 | Should work the search bar | Search bar on the headder part is not working | 1.open the webpage 2.write on the search bar 3.click on the enter or search icon | critical |  |  | New
DEF_HSPS_03 | should work all the links provided | the links provided on the header section is not working | 1.open the webpage 2.click on the space or letters the cursur shows active links | major |  |  | New
DEF_HSPS_04 | should work the facebook link given | the facebook link provided is not working | 1.open the web page 2.click on the facebook icon | major |  |  | New
DEF_HSPS_05 | should work the twitter link | the twitter link given is not working | 1.open the web page 2.click on the twitter icon | major |  |  | New
DEF_HSPS_06 | should work the instagram link | the instagram link given is not working | 1.open the web page 2.click on the instagram icon | major |  |  | New
DEF_HSPS_07 | the phone number given should enable calls directly | the numerals are just characters | 1.open the web page 2.click on the phone number | enhancement |  |  | New
DEF_HSPS_08 | the slide in picture should not delay to show in home page | the slide in pictures are delayed to appear | 1.open the web page 2.click on the home page | minor |  |  | New
DEF_HSPS_09 | the moving link in the home page should be slow | the moving link in the home page "Welcome to our school"is fast | 1.open the web page 2.scroll down the page 3.click on the link | enhancement |  |  | New